## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Member
1.1 | As a member, I can create my own profile | 1 | Zidan
1.2 | As a member, I can view my profile information | 2 | Kilany | 1.1
1.3 | As a member, I can delete my profile | 2 | Zizo | 1.1
1.4 | As a member, I can edit my profile details | 3 | Omneya | 1.1
1.5 | As a member, I can view the available vacancies to be able to apply for it | 5 | Omneya | 3.5 | Omneya
1.6 | As a member, I can create event/workshop/course | 3 | Salma
1.7 | As a member, I can view available locations to be able to book for an event | 5 | Salma | 2.1 | Salma
1.8 | As a member, I can create a new booking request | 5 | Zizo | 1.7 | Salma
1.9 | As a member, I should view notification when the bookings are confirmed | 8 | Zidan | 2.7 | Ahmed H
1.1 | As a member, I should view an updated Booking calender Upon reserving a specified location for an event/workshop/course | 8 | Kilany | 2.7 | Kilany
2 | Partner COworking space
2.1 | As a partner COworking space, I can create my own profile | 1 | Ahmed Amr
2.2 | As a partner COworking space, I can delete my profile | 2 | Hesham | 2.1
2.3 | As a partner COworking space, I can edit my profile information | 3 | Ahmed Amr | 2.1
2.4 | As a partner COworking space, I can view my profile information | 2 | Ahmed H | 2.1
2.5 | As a partner COworking space, I should update my data upon a booking request | 8 | Hesham | 1.8 | Hesham
2.6 | As a partner COworking space, I should view members’ Requests | 5 | Ahmed Amr | 1.8 | Ahmed Amr
2.7 | As a partner COworking space, I should update the information about the booking acceptance | 8 | Ahmed H | 2.6 | Ahmed H
3 | Partner
3.1 | As a partner, I can create my own profile | 1 | Teama
3.2 | As a partner, I can view my profile information | 2 | Teama | 3.1
3.3 | As a partner, I can delete my profile details | 2 | Rana | 3.1
3.4 | As a partner, I can edit my profile details | 3 | Teama | 3.1
3.5 | As a partner, I can post a new vacancy | 3 | Rana
3.6 | As a partner, I can update the vacancy information | 5 | Rana | 3.5
3.7 | As a partner, I can delete an existing vacancy | 3 | Teama | 3.5 | Rana