## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Sheet1
| Table 1 | Sheet1
Sheet2
| Table 1 | Sheet2
Sheet3
| Table 1 | Sheet3

## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As an admin , I should be able to approve any pending registered users so that they can be a part of lirten-hub |  | Abdelrahman Abudif | Amr | Abouismail
1.1 | As an admin, I should be able to delete any vacancies, so that lirten-hub policies are followed. |  | Abdelrahman Abudif | Amr | Abouismail
1.2 | As an admin, I should be able to approve any vacancies, so that lirten-hub policies are followed. |  | Abdelrahman Abudif | Amr | Abouismail
1.3 | As an admin, I should be able to view all events on lirten-hub so that all events created follow policies |  | Abdelrahman Abudif | Amr | Abouismail
1.4 | As a Partner I should be able to create a vacancy so that members can apply for vacancies |  | Hesham | Abdelrahman Abudif | Zidan
1.5 | As a Partner, I should be able to update a posted vacancy, so that members can apply for updated vacancies. |  | Hesham | Abdelrahman Abudif | Zidan
1.6 | As a Partner , I should be able to view all created vacancies, so that I can view all vacancies. |  | Rana | Salma | Omneya
1.7 | As a Partner, I should be able to delete a vacancy, so that only needed vacancies are posted. |  | Rana | Salma | Omneya
1.8 | As a coworking, I should be able to view all coworking so that I can improve my account. |  | Ahmed Abouismail | Hesham | Kilo
1.9 | As a coworking , I should be able to update my coworking information so that they are up to date. |  | Ahmed Abouismail | Hesham | Kilo
2 | As a coworking, I should be able to create an account so that I can be a part of listen-hub |  | Zidan | Teama | Abdelrahman Abudif
2.1 | As a coworking, I should be able to delete my account so that I can be no longer a part of lirten-hub. |  | Zidan | Teama | Abdelrahman Abudif
2.2 | As a Partner, I should be able to view all events so that I can keep track of upcoming events. |  | Salma | Rana | Omneya
2.3 | As a Partner I should be able to update my events so that all events are up to date. |  | Salma | Rana | Omneya
2.4 | As a Partner , I should be able to delete an event so that no longer needed events are not viewed |  | Salma | Rana | Omneya
2.5 | As a Partner, I should be able to create my account so that I can join listen-hub |  | Salma | Rana | Omneya
2.6 | As a member, I should be able to create my account so that I can join lirten-hub. |  | Kilo | Amr | Zidan
2.7 | As a member , I should be able to delete my account so thatI can leave lirten-hub. |  | Kilo | Amr | Zidan
2.8 | As a member, I should be able to update my account so that my information is up to date. |  | Teama | Abdelrahman Abudif | Ahmed Abouismail
2.9 | As a member I should be able to view my profile and other members profile. |  | Teama | Abdelrahman Abudif | Ahmed Abouismail
3 | As a Partner I should be able to view my profile and the Partners profiles so that I can improve my account. |  | omneya | Salma | Rana
3.1 | As a Partner, I should be able to delete my profile so that I can leave lirten-hub. |  | omneya | Salma | Rana
3.2 | As a Partner, I should be able to update my profile, so that my account is up to date. |  | amr | Hesham | Teama
3.3 | As a Partner, I should be able to create my account so that I can join lirten-hub. |  | Amr | Hesham | Teama