## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a partner, I can create an event, so that I can register all the events information. | 3 | Salma | Rana | Omneya
1.1 | As a partner, I can delete an event, so I can erase an event created. | 3 | Salma | Rana | Omneya
1.2 | As a partner, I can update an event, so I can update any information in my event. | 3 | Salma | Rana | Omneya
1.3 | As a partner, I can view an event, so I can see the event created. | 3 | Salma | Rana | Omneya
1.4 | As a partner, I can view all my events, so I can view all my created events. | 3 | Salma | Rana | Omneya
1.5 | As a user, I can search for an event using the location, so I can get the event I want. | 5 | Salma | Rana | Omneya
1.6 | As a user, I can search for an event using the date, so I can get the event I want. | 5 | Salma | Rana | Omneya
1.7 | As a member, I can apply for an event, so I can register for a posted event. | 5 | Salma | Rana | Omneya
1.8 | As a partner I should be able to create a profile | 3 | Omneya | Salma | Rana
1.9 | As a partner I should be able to update my profile so that I can keep my profile updated | 3 | Teama | Kelo | Zizo
2 | As a partner I should be able to delete my profile so that I can no longer be part of lirten-hub | 3 | Omneya | Salma | Rana
2.1 | As a partner I should be able to read my profile so that I can check my own profile | 3 | Teama | Kelo | Zizo
2.2 | As a member I can view my vacancies so that all vacancies are shown. | 5 | Teama | Kelo | Zizo
2.3 | as a partner i should be able to view the applicants on my vacancies so that i can know who is applying for the job | 5 | Teama | Kelo | Zizo
2.4 | As a partner i can be searched by my organization name, email, description, partners so i can be viewed by a lirten hub user | 5 | Omneya | Salma | Rana
2.5 | As a partner I can be searched by board members, field of work and status so i can be viewed by a lirten hub user | 5 | Omneya | Salma | Rana
2.6 | as a partner i should be able to login. | 5 | Omneya | Salma | Rana
2.7 | as a partner i should be able to view all partners | 3 | Omneya | Salma | Rana
2.8 | As a member I should be able to create a profile so that I can be a lirten-hub user. | 3 | Amr | Zizo | Hesham
2.9 | As a member I should be able to update my profile so that I can keep my profile updated. | 3 | Kelo | Ahmed Hisham | Zidan
3 | As a member I should be able to delete my profile so that I can no longer be part of lirten-hub. | 3 | Kelo | Ahmed Hisham | Zidan
3.1 | As a member I should be able to read my profile so that I can check my own profile. | 3 | Amr | Zizo | Hesham
3.2 | As a member I can view my recommended vacancies so that I can find suitable jobs for me easily. | 5 | Kelo | Ahmed Hisham | Zidan
3.3 | As a member I can be searched by my first name, last name, age, email and skills so that I can be viewed by a lirten-hub user. | 5 | Kelo | Ahmed Hisham | Zidan
3.4 | As a member I can be searched by my, interests, work completed, reviews and status so that I can be viewed by a lirten-hub user. | 5 | Amr | Zizo | Hesham
3.5 | As a member I can login to my account so that I can view my profile. | 3 | Amr | Zizo | Hesham
3.6 | As a vacancy, I can be created by a partner | 5 | Hesham | Zizo | Amr
3.7 | As a vacancy, I can be deleted | 3 | Rana | Salma | Omneya
3.8 | As a vacancy, I can be updated | 3 | Hesham | Zizo | Amr
3.9 | As a vacancy, I can be viewed | 3 | Rana | Salma | Omneya
4 | As a vacancy, I can be applied for by a member. | 5 | Hesham | Zizo | Amr
4.1 | As a user, I can search for a vacancy using the location, so I can get the vacancy I want. | 5 | Hesham | Zizo | Amr
4.2 | As a user, I can search for a vacancy using the start date, so I can get the vacancy I want | 5 | Rana | Salma | Omneya
4.3 | As a user, I can search for a vacancy using the end date, so I can get the vacancy I want. | 5 | Rana | Salma | Omneya
4.4 | As a user, I can search for a vacancy using the duration, so I can get the vacancy I want | 5 | Hesham | Zizo | Amr
4.5 | As a coworking , I should be able to view my data so that a partner can reserve a room. | 3 | Zidan | Kelo | Teama
4.6 | As a coworking, I should be able to filter my data so that a partner can view the best option faster. | 5 | Zidan | Kelo | Teama
4.7 | As a coworking, I should be able to view other coworkings so that I can be able to improve my service | 3 | Zidan | Kelo | Teama
4.8 | as a coworking, I should be able to edit my information so that user view updated information. | 3 | Zidan | Kelo | Teama
4.9 | as a coworking, I should be able to post a new room so that reservations increase. | 3 | Ahmed Hisham | Hesham | Zidan
5 | as a coworking, I should be able to edit a specific room info so that users view updated info. | 5 | Ahmed Hisham | Hesham | Zidan
5.1 | as a cowering, I should be able to add a new schedule to my room so that user can view calendar. | 5 | Ahmed Hisham | Hesham | Zidan
5.2 | as a coworking, I should be able to update my reserving info so that user can know reserved slots | 5 | Ahmed Hisham | Hesham | Zidan
5.3 | as a coworking, I should be able to delete my account so that I can be not a part of lirten | 3 | Zidan | Kelo | Teama
5.4 | as a coworking, I should be able to register so that user be able to reserve places | 3 | Ahmed Hisham | Kelo | Zidan
5.5 | As a coworking, I should be able to login so that I can explore lirten. | 3 | Ahmed Hisham | Kelo | Zidan
5.6 | As an admin, I should be able to update my info, so that admins can be updated | 3 | Abdelrahman | Amr | Ahmed hisham
5.7 | As an admin I should be able to delete my profile, so that I can no longer have admin privileges | 3 | Abdelrahman | Amr | Ahmed hisham
5.8 | As an admin I should be able to get my own profile, so that I can check my info | 3 | Abdelrahman | Amr | Ahmed hisham
5.9 | As an admin I can view other admin profiles , so that I can check listen-hub admins | 3 | Abdelrahman | Amr | Ahmed hisham
6 | As an admin , I should be able to approve users after registration | 5 | Abdelrahman | Amr | Ahmed hisham
6.1 | As an admin I should be able to receive requests so that I can approve/disprove them | 5 | Abdelrahman | Amr | Ahmed hisham